## Project Planner
Airbnb Data Analysis Assignment
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 Project Startup | 1 | 2 | 1 | 3 | 100%
1.1.1 Schedule team meeting | 1 | 2 | 1 | 2 | 100%
1.1.2 Define project requirement | 1 | 1 | 1 | 2 | 100%
1.1.3 Choosing additional analysis tool | 2 | 2 | 2 | 2 | 100%
1.1.4 Choosing datasets | 3 | 1 | 2 | 2 | 100%
1.1.5 Choosing additional analysis tool | 3 | 1 | 3 | 1 | 100%
1.2 Setup GitHub Repository | 4 | 1 | 4 | 2 | 100%
1.2.1 Clone provided repo | 4 | 1 | 4 | 1 | 100%
1.2.2 Configure access for team members | 4 | 1 | 4 | 1 | 100%
2.1 Prepare Project Plan | 4 | 10 | 4 | 8 | 100%
2.1.1 Create Project Overview | 4 | 2 | 4 | 2 | 100%
2.1.2 Design Work Breakdown Structure | 4 | 2 | 4 | 2 | 100%
2.1.3 Activity Time Estimation & Definition | 5 | 2 | 4 | 3 | 100%
2.1.4 Create Gantt Chart & schedule | 8 | 2 | 7 | 2 | 100%
2.2 Software Design | 6 | 6 | 6 | 6 | 100%
2.2.1 System Vision Statement | 6 | 2 | 6 | 2 | 100%
2.2.2 List System Requirements | 7 | 2 | 6 | 4 | 100%
2.2.3 Draft use cases for the software | 9 | 2 | 8 | 4 | 100%
2.2.4 Highlight System Components & software design | 10 | 2 | 8 | 3 | 100%
2.2.5 Initial User Interface Design | 11 | 1 | 10 | 2 | 100%
3.1 Code Software | 14 | 23 |  |  | 0%
3.1.1 System 1: Listing information by Area | 14 | 4 |  |  | 0%
3.1.2 System 2: Distribution of Property Prices | 18 | 3 |  |  | 0%
3.1.3 System 3: Keyword record retrieval | 25 | 2 |  |  | 0%
3.1.4 System 4: Customer comments on cleanliness | 29 | 2 |  |  | 0%
3.1.5 System 5: Listings filter by date | 32 | 3 |  |  | 0%
3.2 Create User Manual | 33 | 3 |  |  | 0%
3.2.1 Draft usage steps | 34 | 2 |  |  | 0%
3.2.2 Include screenshots for software features | 36 | 1 |  |  | 0%
4.1 Software Testing | 37 | 15 |  |  | 0%
4.1.1 Create a testing plan | 37 | 2 |  |  | 0%
4.1.2 Unit testing for each system | 39 | 2 |  |  | 0%
4.1.3 Examine outcomes of test coverage | 40 | 1 |  |  | 0%
4.2 Progress Monitoring | 45 | 5 |  |  | 0%
4.2.1 Update Gantt Chart to reflect actual dates | 47 | 2 |  |  | 0%
4.2.2 Regular team check-ins to adherence adherence to plan | 41 | 9 |  |  | 0%
5.1 Final Documentation | 52 | 8 |  |  | 0%
5.1.1 Update Project Plan with actual data | 52 | 2 |  |  | 0%
5.1.2 Finalize Software Design Document | 53 | 2 |  |  | 0%
5.1.3 Complete User Manual | 55 | 1 |  |  | 0%
5.1.4 Executive Summary data analysis | 53 | 3 |  |  | 0%
5.1.5 Software Testing Report | 54 | 2 |  |  | 0%
5.2 Finalize Commit on GitHub | 55 | 2 |  |  | 0%
5.2.1 Ensure uploading all necessary files | 55 | 1 |  |  | 0%
5.2.2 Update git_log.txt | 56 | 1 |  |  | 0%
5.3 Project Review | 57 | 2 |  |  | 0%
5.3.1 Team meeting to assess project accomplishments. | 58 | 1 |  |  | 0%
5.3.2 Record lessons learned for future projects. | 59 | 1 |  |  | 0%